SUPPLY CONTRACT FOR EUROPEAN

UNION EXTERNAL ACTIONS

No: BicOa Supply HUHR/1101/1.2.2/2008

financed from the EU General Budget

- Hévíz City Municipality

8380 Hévíz, Kossuth Lajos u. 1.

Tax number: 15734374-2-20

Bank account number: 11749039-15432429-10160002

Representative: 	Papp Gábor, mayor

(‘Contracting Authority’)

of the one part,

and

NEUZER Kerékpár Kereskedelmi és Szolgáltató Korlátolt Felelősségű Társaság
Official registration number: 11 09 005003

Full official address: 2500 Esztergom, Mátyás király utca 45.
VAT number: 11196754-2-11

Representative: Neuzer András, managing director

(“the Contractor”)

of the other part,

have agreed as follows:

- “Creation of a bike docking system service for Municipality of Hévíz, which includes bicycles and related equipment, including a vehicle for the transport of bicycles in the framework of the project BicOa, HUHR/1101/1.2.2/2008, HÉVÍZ, Hungary”

- Article 1	Subject

  - The subject of the Contract is the production, delivery, installation, startup and maintenance of the following equipment:

4 docking platforms: The docking platforms consist of terminals, docks and bicycles

- 56 docks

- 4 terminals

- 30 bicycles

1 Management system

1 transporting, bike collecting vehicle, with maintenance equipment

1 Control center (2 hardware, software, with installation and training)

1 Workstation (1 pc. of hardware, software, installation, training)

Delivery, installation and training

Creation of the publicity plan

Other equipment required for operation

1.2.	The accepting place for these equipment is Hungary, Hévíz, Kossuth Lajos street 1., the interval for delivery is 2014.01.01. – 2014.04.30., the Incoterms applied should be DDP. The interval for completing the tasks is expected to be from contracting until 2014.05.30.
The handover of the work area is foreseen to be 2014.03.01., the technical handover’s date is planned to be 2014.04.30.; Workstation, control centers, transport vehicle delivery: from contracting until 2014.02.28.; Production and installing of docking stations, production and delivery of bicycles, installing of the control system: from contracting until 2014.04.30.; Test period: 2014.04.15. -  2014.05.30.

1.3	The Contractor shall comply strictly with the terms of the Special Conditions and the technical annex.

1.4 	The supplies which form the subject of the contract must be accompanied by the spare parts described by the Contractor in its tender and by the accessories / other items necessary for using the goods over a period of 1 year as specified in the Instructions to Tenderers.

Article 2	Origin

The rules of origin of the goods are defined in Article 10 of the Special Conditions.

A certificate of origin for the goods must be provided by the Contractor at the latest when it requests provisional acceptance of the goods, except for the equipment concerned by derogation. Failure to comply with this condition may result in the termination of the contract.

The Contracting Authority gave derogation from the rules of origin to the following equipment: vehicle for the transportation of the bicycles, the hardware and software used.

- Article 3	Price

3.1	The price of the supplies shall be that shown on the financial offer (specimen in Annex IV). The total maximum contract price shall be 154.570 EUR + 27% VAT (196.304 EUR)

3.2 	Payments shall be made in accordance with the General and/or Special Conditions (Articles 26 to 28).

  - The entrepreneurial award provides coverage to the Contractor for all the direct and indirect costs that occur concerning the technical tasks, except for the costs that are borne by the Contracting Authority according to this contract.

The entrepreneurial award consists of:

- the cost of all items in the budget announcement

- costs related to implementation due site characteristics

- costs of temporary side facilities, expenses incurred in connection with the implementation, administrative fees, the cost of restrictions

- the cost of detailed plans necessary for the implementation

- the cost of handover documents, compilation of operating manuals

- costs related to use of public places

- the cost of electricity and water use, waste disposal and transport

- utilization costs for the auxiliary structures and equipment necessary for the implementation

- costs related to environmentalism, conservation and extreme weather

- special charges, surcharges incurred in the process of the implementation

- the cost of quality control.

  - The Contractor confirmed the entrepreneurial award under 3.1 with the tender documentation given by the Contracting Authority and the pricing of the budget which is part of the tender documentation.

  - The plans, technical documentation and technical specifications which are parts of the tender documentation and provide the basis of this contract were revised and were commented on by the Contractor. The costs including the cost of the adjunct tasks were cross-checked before the signing of this contract by the Contractor, because of this the Contractor cannot ask coverage for additional costs and have quantitative complaints towards the Contracting Authority in the project implementation process referring to the deficiency of the documentation after signing this contract. These objections and claims also cannot be made if the Contractor hasn’t practiced his rights for remarks properly.

  - With the completion of the Contract the Contractor provides the Contracting Authority with the establishments in their intended state and suitable for use. The Contractor bears all risks deriving from the misinterpreting of the tender documentation.

3.7 The Contractor can only deviate from the structures, technical contents and materials described in the technical documentation and budget (which provide the base of this contract), if the technical supervisor of the Contracting Authority gives him written permission before doing so, even if the Contractor uses an equivalent alternative solution.

- Article 4	Order of precedence of contract documents

The contract is made up of the following documents, in order of precedence:

- the contract agreement;

- the Special Conditions

- the General Conditions (Annex I);

- the Technical Specifications (Annex II [including clarifications before the deadline for submission of tenders and minutes from the information meeting/site visit];

- the Technical Offer (Annex III [including clarifications from the tenderer provided during tender evaluation];

- the budget breakdown (Annex IV);

- (specified forms and other relevant documents (Annex V));

- The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. In case of replacements the order of precedence of modified documents should follow the original order of precedence of contract documents.

- This Contract was signed by both parts according to their intentions. This Contract takes effect after the Contractor signs it.

- This Contract was written in English, in six originals, of which four originals are kept by the Contracting Authority and two originals are kept by the Contractor.

| For the Contractor |  | For the Contracting Authority |  |
| --- | --- | --- | --- |
| Name: | Neuzer András | Name: | Papp Gábor |
| Title: | managing director | Title: | mayor |
| Signature: |  | Signature: |  |
| Date: | December 2013. | Date: | December 2013 |

# SPECIAL CONDITIONS

- CONTENTS

These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions. In exceptional cases, and with the authorisation of the appropriate Commission departments, other clauses may be added to cover specific situations.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communications

All written communication between the Contracting Authority and the Contractor connected to this Contract should contain the name and identification number of the Contract, the means of communication are: postal, fax, e-mail and personal.

Representation of the Contracting Authority

Both parts agree that concerning the completion of the Contract:

Of the part of the Contracting Authority:
Gábor Papp, mayor

Of the part of the Contracting Authority the following person can give a certificate of compliance:
József János Kepli, vice mayor

Technical contact of the Contracting Authority:

Name: Ottó Vasas, investment administrator
Phone number: +36-83/500-840
E-mail: vasas.otto@hevizph.hu

Representatives of the Contractor:

In matters concerning the Contract

Name: ………………………………….

Address:………………………………….

Phone number: ……………………………..

E-mail:	……………………………….

Of the part of the Contractor the following person can give a certificate of compliance:

Name: ………………………………….

Address:………………………………….

Phone number: ……………………………..

E-mail:	……………………………….

Article 6	Subcontracting

Subcontracting is allowed. The Contractor is responsible for his legally employed subcontractors, like he would have done their work himself. The illegally employed subcontractors a responsible for all the damage which wouldn’t have occurred without their employment.

Article 7	Supply of documents

Documents supplied by the Contractor: technical/operational description, brochure, user’s manual in Hungarian.

Article 8	Assistance with local regulations

According to the Hungarian law the equipment cannot be put into operation without the following document: installation and commissioning license

Article 10	Origin

## 10.1	All goods purchased must originate in a Member State of the European Union or a country covered by the Hungary-Croatia IPA Cross-border Co-operation Programme 2007-2013. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or to the relevant international agreement applicable.

The Contracting Authority gave derogation from the rules of origin to the following equipment: vehicle for the transportation of the bicycles, the hardware and software used.

Article 11	Performance guarantee

11.1	The Contractor guarantees that the tools, equipment, and the used, built-in materials can only be of first class quality. The establishments will be built keeping the Hungarian Standards and regulations concerning the used materials, the structure and of the outlook of establishment too.

11.2	The Contractor holds a 1 year long warranty period after the handover-takeover for the completion of the contents written in Article 1.

11.3	The Contracting Authority is responsible for the reporting of deficiencies occurring to in the warranty period towards the Contractor immediately, but at the latest until the end of the 1 year warranty period. The Contractor is responsible for the forthwith repair or replacement after the error has been reported. If the Contractor cannot repair or replace the deficiencies within 8 days of the error report, the Contracting Authority is allowed to make the repair/replacement with another implementer, and the costs of this implementation have to be paid by the Contractor.

11.4  Faulty performance penalty:

Requirements: contractor does not fulfill his responsibilities under this contract agreement and doesn’t correct errors indicated by the Contract Authority.

Rate: from the day after the expiring of the error-correcting period, 1% of the penalty base daily, up to the maximum 20% of the penalty base.

11.5  Delay penalty:

Requirements: the Contractor fails to complete his tasks in time according to the schedule.

Rate: 1% of the penalty base daily, up to the maximum 20% of the penalty base. After 30 days of delay the Contracting Authority is allowed to terminate the contract unilaterally.

11.6  Failure penalty:

Requirements: the Contractor fails to complete his tasks (or parts of his tasks), including the case if the Contractor fails to complete them in time according to the schedule, and the compliance is no longer required by the Contracting Authority.

Rate: 20% of the penalty base.

The Contractor agrees that the Contracting Authority can deduct the sum of the penalty from the invoice. The base of the penalty is the entrepreneurial award increased with VAT.

Article 12	Insurance

The Contractor has full compensation liability for all the damage occurring in the completion process of the Contract and that is connected to his activity. The Contractor should have a C.A.R. (Contractors All Risk) total risk system construction and installation insurance concluded or expanded for the task in this Contract with the sum of 45 million HUF/year and 15 million HUF/disservice for building construction and non-property damage liability insurance until the time of the handover-takeover. The liability insurance should cover the liability for the damage caused by the Contractor and the subcontractors too. The bond certifying the liability insurance should be shown until the signing of the Contract. The insurance covers the risks concerning the building and installment works according to the entrepreneur and insurer practice and experiences.

Article 13	Programme of implementation of tasks

13.1 Creating a publicity plan: from contracting until 2014.01.15.

Workstation, control centers, transport vehicle delivery: from contracting until 2014.02.28.

Partial completion deadline: 2014.02.28.

Production and installing of docking stations, production and delivery of bicycles, installing of the control system: from contracting until 2014.04.30.

Test period: 2014.04.15. - 2014.05.30.

Completion deadline: 2014.05.30.

13.2 The Contracting Authority accepts completion before the deadlines.

13.3 In case of delay correlated to the deadline the Contractor must pay a delay penalty.

13.4 The rate of the delay penalty is: 300.000 HUF/day, concerning the partial completion deadline: 100.000 HUF/day, which can be asked to be paid by the Contractor to the Contracting Authority. The Contracting Authority is allowed to deduct the sum of the penalty from the (final) invoice.

Article 14	Contractor’s drawings

14.1	The Contractor supplies:

- the user’s manual, user interface (printed and software/digital version) in Hungarian, English, German and Russian languages

- service interface user’s manual in Hungarian

- publicity plan

Article 15	Sufficiency of tender prices

Not relevant!

Article 17	Patents and licences

Not relevant!

Article 18	Commencement order

Immediately after signing the Contract by both parties.

Article 19	Period of implementation of the tasks

19.1	The Contract period is expected from the signing of the Contract until 2014.05.30., which is the last deadline for the technical handover-takeover.

Article 22	Amendments

22.2	The Contracting Authority reserves the right to vary by administrative order the quantities specified by +/- 10 % at the time of contracting and during the validity of the Contract. The total value of the supplies may not rise or fall as a result of the variation of the quantities by more than 25 % of the tender price. The unit prices quoted in the tender will be multiplied by the revised quantities procured under the variation.

Article 24	Quality of supplies

24.2	The planned time of technical and technological handover-takeover: 2014.04.30.

Article 25	Inspection and testing

25.2	Planned test period: 2014.04.15. – 2014.05.30.

Article 26	General principles for payments

26.1	Payments shall be made in euros.

The Contracting Authority does not pay in advance.

Upon completion, it is possible to give in a partial or final invoice, which becomes due if the Contracting Authority gives a certificate of completion about it as the following:

1. part: 2014.02.28, 30% of the total sum.

After the completion of tasks according to schedule and presenting the partial invoice the Contractor should receive 30% of the entrepreneurial award.

Final invoice 2014. 05 30, 70% of the total sum.

After the completion of tasks according to schedule and presenting the partial invoice the Contractor should receive 70% of the entrepreneurial award.

The invoices should be addressed to Hévíz City Municipality (Contracting Authority), the issuer has to write the registration number of the Contract on the invoice.

The entrepreneurial award is paid by the Contracting Authority to the Contractor according to the given invoice by bank transfer. The flawlessly filled invoice must be paid to the Contractor by the Contracting Authority within 15 days of receiving it. The deadline for the payment of the final invoice can be shorter concerning the project completion deadline and the accounting of the sum of the final invoice.

The certificate of origin given by the Zala County Chamber of Trade and Commerce has to be submitted before the provisional acceptance of the Contracting Authority.

The Contracting Authority gave derogation from the rules of origin to the following equipment: vehicle for the transportation of the bicycles, the hardware and software used.

26.5	In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the General Conditions, once the deadline laid down in Article 26.3 has expired, the Contractor will, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.2	The Contractor bears all risks concerning the products until they arrive to preliminary affiliation. The products should be wrapped up while being transported to prevent possible damage and abuse.

29.3	The packaging will become the property of the recipient subject to environmental considerations.

29.4 	There are no special requirements for single transportation, but the official IPA stamp has to be placed on the products (see the Project Communication Guidelines http://www.hu-hr-ipa.com/en/downloads)

29.5	The handover-takeover of the establishment:

The Contractor should notify the Contracting Authority about the completion of the tasks via a written reporting letter at least 8 days before the completion. The Contracting Authority has to specify the time of the handover-takeover procedure within 7 days upon receiving the report letter about the completion of the tasks, the Contracting Authority also has to invite the competent authorities until this deadline.

The authority statements required for the startup and operation deriving from the entrepreneurial activity should be ensured by the Contractor. The technical completion ends with the closing of the handover-takeover process, the completing of the contract is finished by ensuring the conditions of startup.

Article 31	Provisional acceptance

The Certificate of Provisional Acceptance must be issued using the template in Annex C11.

The Contractor has to submit the certificate of origin given by the Zala County Chamber of Trade and Commerce before the provisional acceptance. The certificate of provisional acceptance isn’t possible without the certificate of origin.

Article 32	Warranty obligations

32.6	The Contractor has to guarantee that the equipment are new, not used, are the newest models and fuse the newest developments in design and materials. The Contractor has to guarantee that the equipment don’t have deficiency in design, material or elaboration. The warranty has to be valid for maximum 1 year after the provisional acceptance.

32.7	The warranty must remain valid for one year after provisional acceptance. The contents and indicative price of the extra warranty services offered after the compulsory one year warranty should be drawn up in an informative manner for 3 years.

Article 40	Settlement of disputes

40.4	Any disputes arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of Zala County Court in accordance with the national legislation of the state of the Contracting Authority.

- * * *

<DDP (Delivered Duty Paid – Leszállítva vámkezeléssel) - Incoterms 2010 Nemzetközi Kereskedelmi Iparkamara - http://www.iccwbo.org/incoterms/